## Sheet1
Week 1 |  | Get to now the subject and form a research question
Week 2 | 2015-11-30 | Implement the 'must haves' tools in script
| 2015-12-01 | Implement the 'must haves' tools in script
| 2015-12-02 | Check and validate output
| 2015-12-03 | See if matches of genes can be found within the metabolic pathway
| 2015-12-04 | Presentations
Week 3 | 2015-12-07 | Optimize the code with 'should haves' and maby 'could haves'
| 2015-12-08 | Optimize the code with 'should haves' and maby 'could haves'
| 2015-12-09 | Check and validate output
| 2015-12-10 | See if matches of genes can be found within the metabolic pathway
| 2015-12-11 | Run the code with the real dataset
Week 4 | 2015-12-14 | Perfecting the code
| 2015-12-15 | Writing report
| 2015-12-16 | Writing report
| 2015-12-17 | Writing report
| 2015-12-18 | Presentations